## Title
Field | Value
Project Name | Construction of Rural Road Network Phase II
Contractor Name | ABC Construction Pvt. Ltd.
Agreement No | AGR/2024/001
Work Order No | WO/2024/RRN/001
Location | Village Khemnagar, Udaipur
Division | PWD Division Udaipur
Estimated Cost | 5000000
Start Date | 01/01/2024
Completion Date | 31/12/2024

## Work Order
S.No. | Item Description | Unit | Quantity | Rate | Amount
1 | Excavation in ordinary soil | Cum | 500 | 150 | 75000
2 | Providing and laying cement concrete 1:2:4 | Cum | 200 | 4500 | 900000
3 | Providing and laying bituminous concrete | Cum | 150 | 6500 | 975000
4 | Construction of side drains | Rmt | 1000 | 200 | 200000
5 | Road marking and signage | Sqm | 50 | 250 | 12500

## Bill Quantity
S.No. | Item Description | Unit | Executed Quantity | Rate | Amount
1 | Excavation in ordinary soil | Cum | 480 | 150 | 72000
2 | Providing and laying cement concrete 1:2:4 | Cum | 195 | 4500 | 877500
3 | Providing and laying bituminous concrete | Cum | 145 | 6500 | 942500
4 | Construction of side drains | Rmt | 980 | 200 | 196000
5 | Road marking and signage | Sqm | 48 | 250 | 12000

## Extra Items
S.No. | Item Description | Unit | Quantity | Rate | Amount
1 | Additional culvert construction | Each | 2 | 25000 | 50000
2 | Extra retaining wall work | Sqm | 50 | 1200 | 60000